ANNUAL PROGRAMME 2010

REVISED VERSION

Athens 25-06-2012

MEMBER STATE:                   GREECE

FUND: 		             EUROPEAN RETURN FUND

RESPONSIBLE AUTHORITY:  MINISTRY OF CITIZEN PROTECTION / HELLENIC POLICE      HEADQUARTERS/FINANCE DIVISION

YEAR COVERED:		   2010

1.	GENERAL RULES FOR SELECTION OF PROJECTS TO BE FINANCED UNDER THE PROGRAMME

1.1. INTRODUCTION OF THE IMPLEMENTATION METHODS TO BE USED

For the implementation of the 2010 Annual Program, , the Responsible Authority will act both as awarding and executing body (Articles 7, 8 and 9 of the E 2008/796/EC implementing rules decision).

Due to the exclusive competences of the Hellenic Police concerning the return area where the legal monopoly for the specific law enforcement authority exists, for the majority of actions proposed in the 2010 annual programme the Responsible Authority will act as an executing body apart from the actions relating to voluntary returns.

For the implementation of actions relating to voluntary returns, the Responsible Authority will act as an awarding body. The Responsible Authority will coordinate the selection process (please see section 1.3.) and will monitor the implementation of grant agreements by the final beneficiaries.

With a view to strengthening the management and control system and in order to facilitate the tasks of the Responsible Authority concerning the monitoring of the appropriate arrangements, following the adoption of the programme the Responsible Authority will sign written agreement with the competent representative of the Hellenic Police Headquarters (memorandum of understanding ) and final beneficiaries (Grant Agreement). These agreements will state all the details relating to the performance of the duties and obligations which are being delegated to the competent Divisions of the HPHQ and final beneficiaries, such as the monitoring and development of the implementing actions via periodical reports (monthly – quarterly) which will be submitted to the R.A. by the competent body.

Furthermore, the RA will have access in all files, which the competent Services keep concerning the implementation of the actions in order the RA can implement verifications of provided elements, after controls on the spot in application of article 27 of the Basic Act.

This will facilitate the work of the responsible authority, which will have the final responsibility for the implementation of the multiannual programme.

1.2. JUSTIFICATION OF THE EXECUTING BODY METHOD

Under Law 2800/2000 (Government Gazette I 41/29.02.2000), “Restructuring of departments of the Ministry of Public Order, establishment of the Hellenic Police HQ, and other provisions” and Presidential Decree 14/2001 (Government Gazette I 12/31.01.2001), the Hellenic Police is responsible for the issues relating to the entry, residence and, in cooperation with the rest competent national authorities, employment of foreign nationals in Greece, except in areas under the jurisdiction of the Coast Guard and for the returns of the  arrested illegal immigrants in the whole land.

According to the contents of the decision on the European Return Fund, the entire territory of Greece is an eligible area for financial assistance through the Fund. So the actions, describing in the annual programme of 2010 will be implemented only by the competent Divisions of the Hellenic Police Headquarters, under the surveillance and the guidance of the Responsible Authority. So the Responsible Authority will implement the projects of the actions of the annual programs jointly (indirectly):

- With Divisions of the Hellenic Police Headquarters, because of the technical expertise, high degree of specialization and administrative powers of the services per category of actions.

The Directorate of Police Headquarters that involve jointly with the responsible authority to the implementation of the actions of the annual programs are as below :

The Department of Foreigners that is responsible for the study of subjects for aliens, the preparation of legislation, the administrative operations, the process of the rules and measures, the guidance regional brigades in the implementation of existing immigration laws and particularly the handle of issues, the passport control, the  operation of the responsible departments for passport control, the cooperation with the authorities that are responsible to approve the arrival of foreigners to work, study, cultural events, family reunification and other projected cases from the law, for reasons public order an safety, the except at the entrance of aliens who do not meet the conditions of entrance, etc.

The Directorate of Civilian Personnel that deal issue of postings, accessions, transfers, demotions, placing of duty, experience, index qualification and scores work, evaluation of positions, reports police personnel capacity and ability, grade and salary promotions, leave, sickness, moral pay, disciplinary and criminal cases, licenses of exercise work for pay, layoffs, placements, transfers, secondments, temporary movements and any other matter that is related to the permanent civilian personnel, the concern for the issue of administrative acts, etc.

The Directorate of Education that is responsible for the appointment of teachers, trainers and other personnel in the training schools, the approval of training programs that are developed by the Police Academy, the issue or supply of textbooks and teaching aids for the needs of training for the police personnel with the cooperation Departments of Greek Police Headquarters on issues of international and European courses, the study, the treatment and the development at training and advanced level of the reports that are submitted by participants at international and European educational programs and the creation one database relevant to this, the monitoring and evaluation programs of personnel training at International and European level and the classification based on the Knowledge of the subject, etc.

The sudden and dramatic increase of accumulation of immigrants has created many problems since a large part of the specific migrations flows comes mainly from underdeveloped countries. The arrested illegal immigrants should be returned to their countries of origin or third countries that would accept them. In order to be achieved effectively the management of return is necessary the implementation of the acts where the Responsible Authority acts as executing agency therefore because of monopoly law the particular responsibility has only the Greek Police.

On the occasion the syntax of the budget that starts from May through July each tear all the Directorates of Greek Police make planning activities for the next year. The responsible Authority chooses actions that are eligible and can be financed by the Fund.

On voluntary returns the responsible authority acts as an awarding body and is designed to provide the effective mechanisms and procedures for the safe, organized and dignified return of third country nationals wishing to return to their country.

The implementation of annual programs of European Return Fund which acts as an executive body made jointly with the Directorates of the Hellenic Police Headquarters, which is represented by the Chief of the Hellenic Police. The Chief will sign the Memorandums of Understanding and will commit to the successful completion of projects.

1.3. THE SELECTION PROCEDURES APPLIED

The actions concerning the 2010 Annual Program have been chosen exclusively from the actions described in the M.A.P. of the European Return Fund.

Executing body method

The selection process for actions to be implemented under the executing body method was done at the moment of the drafting of the 2010 annual program and the following competent national services of the Ministry of Citizen Protection/Hellenic Police Headquarters were involved: the Aliens Division, the Civil Personnel Division, the Training Division of the HPHQ.

The Responsible Authority (the Finance Division of the HPHQ) prepared a document, referring to the eligible actions and the strategic guidelines (priorities – specific priorities) of the European Return Fund and calling for the submission of proposals for potential actions. Following the assessment of the Monitoring Committee of the submitted proposals, the selected actions were taken into account for the draft 2010 Annual Programme. It is assumed that these services will implement the decided actions in association with the RA.

Awarding body method

For the action involving voluntary returns, final beneficiaries will be selected following an open call for proposals. The invitation for submitting proposals will be widely circulated to potential final beneficiaries (e.g. publication in main daily newspapers and the site of the Fund). The call for proposals will include the description of possible projects, references to the legal framework, the available budget as well as the financial plan, potential final beneficiaries, the type and methodology for the evaluation and selection of the proposals, qualitative and quantitative indicators that for monitoring, the symbols of European Union and Hellenic Republic, the place and time for the submission of the proposals, the attached documents and any other necessary element.

A Special Evaluation Committee responsible for the evaluation of the proposals submitted for co-financing under the Fund will be set up. The Responsible Authority will coordinate and provide support to all the stages of the selection process, in particular, The RA will

- Organize and publicize invitations for submitting proposals.

- Draw up an approval decision on selected projects taking into account the opinion of the Special Evaluation Committee,

- Ensure the preparation and signature of grant agreements between the RA and the legal representatives of final beneficiaries.

- Monitor the implementation of the actions approved in the framework of the multiannual programme and the annual programmes.

The Approval Decision will be published on the website of the Return Fund and will be announced to all the applicants (who are also informed about the results of the selection procedure). It will be also registered in the Monitoring and Accounting System for the Return Fund (M.A.SY.RE.F). Also, Grant Agreements will be registered in the Monitoring and Accounting System for the Return Fund (M.A.SY.RE.F).

1.4. IMPLEMENTATION PROCEDURES

Regarding the procedures for the implementation of the actions, the Responsible Authority will apply the national legislation about the public accounting (Law of 2362/95 Government Gazette 247/A - 27-11-1995 and others) which is in compliance with article 11 of the implementing rules (Decision 2008/458/EC), with the exception of the different provisions on the thresholds determining the kind of procedures to be followed, such as regular procurement procedure (open or restricted) or concise process (direct entrusting, makeshift or negotiated).

The majority of the proposed actions concern the provision of services and not procurement procedures. According to the above mentioned Law and the relevant ministerial decisions, all the procedures concerning the provision of services for public bodies are implemented by the own public service of our country. Thus, the Responsible Authority will commit, via the signature of memorandum of understanding, to the competent, for each action, Service of the HPHQ, the implementation of all procedures either concerning procurement or the provisions of services.

According to the above mentioned Law (L. 2362/95 Government Gazette 247/A - 27-11-1995) and the relevant ministerial decisions, all the procurement procedures concerning the equipment’s supplying for public services of Budget from 45.000 Euros and above, are held by the Ministry of Economy, Competitiveness and Mercantile Marine of our country. Nevertheless, the public services are able to ask from the Ministry of Economy, Competitiveness and Mercantile Marine the issuing of authorisation, with result the above processes to be realised by them and not by the central service of the above-mentioned Ministry. Thus, the Responsible Authority, will commit, via the signature of memorandum of understandings, to the service of Supplies of the Hellenic Police Headquarters, either the realisation of all procedures concerning procurement procedures and implementation of conventions, provided that is granted relative authorisation from the Ministry of Economy, Competitiveness and Mercantile Marine or the monitoring of the implementation course of the above processes that will be realised by the responsible service of the Ministry of Economy, Competitiveness and Mercantile Marine .

If the procurement procedures will be assigned to the competent service of the Hellenic Police Headquarters and not to the Ministry of Economy, Competitiveness and Mercantile Marine the contracts of the procurement procedures will be signed, proportionally to the amount of the contract, by the political or natural leadership of the Ministry of Citizen Protection/Hellenic Police Headquarters, according to the national legislation, in which will be assigned additional duties by the Responsible Authority.

Actions 3.1.1. and 3.1.2. will be implemented by another procedure which is the ‘' work contract ‘’(Article 6 of Law 2527/97 Government Gazette 206/Volume Α/08.10.1997). This will involve a Common Ministerial Decision issued and signed by the Minister of Citizen Protection and any other relevant Minister which will specify the following elements:

- the number of persons to be occupied,

- the project to be executed,

- the period of time required for a complete or staggered project delivery,

- the total amount of the contractor’s remuneration,

- the place of the project’s execution and

- any other terms and details in relation to the contractors’ rights and  obligations.

The implementation of the Programme will start right after the approval of the 2010 annual programme by the European Commission according to the time schedule presented hereafter.

| ##### Indicative Timetable for the implementation of actions |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Selection procedures/ (Call for Proposals) | Signatures of memorandums of understanding/ Grant agreements | Implementation of action | Closure of action |
| Action 3.1.1. | 11.2010 | expected in 12.2010/1.2011 | 01.2011-06.2012 | 06.2012 |
| Action 3.1.2. | 11.2010 | expected in 12.2010/1.2011 | 12.2010-06.2012 | 06.2012 |
| Action 3.1.3. | 11.2010 | expected in 12.2010/1.2011 | 01.2011-06.2012 | 06.2012 |
| Action 3.1.4. | 11.2010 | expected in 12.2010/1.2011 | 01.2011-06.2012 | 06.2012 |
| Action 3.1.5. | 11.2010 | expected in 12.2010/1.2011 | 01.2011-06.2012 | 06.2012 |
| Action 3.1.6 | 11.2010 | expected in 12.2010/1.2011 | 12.2010-06.2012 | 06.2012 |
| Action 3.1.7 | 11.2010 | expected in 12.2010/1.2011 | 01.2011-06.2012 | 06.2012 |
| Action 3.1.8 | 04.2012 | expected in 04.2012/05.2012 | 04.2012-06.2012 | 06.2012 |
| Action 3.2.1. | 11.2010 | expected in 12.2010/1.2011 | 01.2011-06.2012 | 06.2012 |
| Action 3.3.1. | 11.2010 | expected in 04.2011/05.2011 | 05.2011-06.2012 | 06.2012 |
| Action 3.4.1. | 11.2010 | expected in 12.2010/1.2011 | 01.2011-06.2012 | 06.2012 |

2.	CHANGES IN THE MANAGEMENT AND CONTROL SYSTEMS (if appropriate)

Following the governmental restructuring in 2009, the Hellenic Police as whole entity falls now under the new Ministry of Citizen Protection, not the Ministry of Interior. However, the Responsible Authority is currently preparing a proposal for the revision of the Management and Control System in particular making a new arrangement under the organisation of the RA. Once the proposal for the new MCS description would be mature, the RA will submit it for the approval of the Commission.

- ACTIONS TO BE SUPPORTED BY THE PROGRAMME UNDER THE PRIORITIES CHOSEN

  - Actions implementing priority 1

3.1.1. The improvement of the information provided to potential returnees, by the employment of interpreters and translators of their languages (Objective 1 under priority 1 of the Multiannual Programme ( MAP))

3.1.1.1. Purpose and scope of the action

A large number of illegal immigrants come mainly from countries of Asia and Africa and they do not speak any language except their native language. Therefore, their communication with the Greek authorities is very difficult. In order to facilitate this communication the existence of interpreters is necessary. Their duties are focused on:

- The translation and explanation, to the potential returnees, of their rights, the reasons of their arrest and the return to their countries of origin.

- The verification of the nationality, which the returnee has declared.

The interpreters will cover a wide network of nationalities, languages and dialects (e.g. Farsi, Urdu, Pashtu, and Arabic). Their total will reach 60 interpreters who will be allocated as follows:

- In Athens ( Aliens’ Directorate of Attica )

- In the Police Directorate of Orestias

- In the Police Directorate of Lesvus

- In the Police Directorate of Samos

- In the Police Directorate of Chios

- In the Police Directorate of Dodecanese

- In the Police Directorate of Achaia

This action implies a continuation of action included in annual programme 2008 and 2009. However, this action was not implemented under the 2008 AP since the necessary joint ministerial decision by the Greek legislation was not signed on time due to governmental and legislative changes.The selection procedure, for the employment of the above mentioned personnel, is in process and hasn’t been finished yet, for the annual programme 2009.

In addition, this action is also included in the Greek Action Plan on the management of migration flows presented by the Greek Government in August 2010. It is expected that the implementation of this action will significantly contribute to addressing the needs indentified in the Action Plan.

The implementation of the action under the 2010 AP will start after the approval of the 2010 Annual Program. Due to the national legal requirements, the recruitment process will be subject to a new selection procedure. The action will finish by 30-06-2012.

3.1.1.2. Expected grant recipients

The Responsible Authority will implement this action in association with  the appropriate Divisions of the Hellenic Police Headquarters of the Ministry of Citizen Protection.

3.1.1.3. Where appropriate, justification regarding project(s) implemented directly by the responsible authority acting as an executing body

The Ministry of Citizen Protection (Finance Division at Hellenic Police Headquarters) may act as the executing body of projects co financed by the European Return Fund where the project comes under its exclusive authority as the national public body and cannot be allocated to another agency or authority. According to our national legislation [articles 8 and 15 of the Presidential Decree 14/2001 (Government Gazette I 12/31.01.2001)], the Ministry of Citizen Protection / Hellenic Police Headquarters / Finance Division, Aliens Division and Civil Personnel Division will implement the above-mentioned action.

3.1.1.4. Expected quantified results

The expected results from the implementation of the said action will be the following:

- the reduction of the problems caused by the arrested illegal immigrants to be returned, as they will understand their rights, the reasons why they are in detention and the procedures of their return;

- the respect of human rights;

- a quicker dispatch of the various cases and

- the upgrading of the services provided by the Hellenic Police to the persons to be returned.

3.1.1.5. Indicators to be used

Output: Number of interpreters’ employment.

Outcome: Upgrade of the provided services to the potential returnees, faster procedures for return management.

Impact: Development of the return management’s effective application.

3.1.1.6. Visibility of EC funding (Pertinent for all proposed actions in the Annual Programme 2009)

The annual programme will be published on the official website of the Ministry of Citizen Protection as and when it is approved.

Publication of the objectives and instruments of the European Return Fund is designed to:

- inform public opinion in general about the role played by the European Union and the Greek authorities in the programme and the results of its implementation;

- inform the public in general at central and regional level about the objectives, aims, priorities and actions of the Fund and the level of EC co financing through a selection of communication and promotional actions;

- guarantee actions under the programme are visible by providing a full range of information for all social agencies.

Consequently, the aim of valid and prompt information and publication is to achieve transparent and effective management of national and Community resources.

For the purposes of information and publicity measures concerning the Fund, the responsible authority set up under law 3613/07 (Government Gazette 263/I/23.11.2007) will publish, according to the above mentioned procedure, notices of each scheduled competition in the daily Greek press and in the Official Journal of the European Communities.

Each communication action will include clear information on the participation of the EU (mainly in the form of a reference to the contribution of the EU and the percentage of assistance for the actions being promoted) and the European emblem/logo will appear alongside every national emblem/logo.

Information plaques or stickers will be attached to all types of equipment for co financed actions, depending on the type of equipment. One part of the plaque or sticker will be used to advertise the EU contribution (and specifically the External Borders Fund) by including a description in words and the Greek flag and the EU emblem/logo, as stipulated in Article 35 of Commission decision no. E (2008) 796/5-3-2008 on the implementation rules for Decision 575/2007/ΕC establishing the European Return Fund.

The regulatory framework governing information and publicity of actions under the programme is set out in the above Commission decision (Articles 31-35) and is concerning the Responsible authority and the other final beneficiaries, because the RA will act both as an executing and awarding body. The visibility guidelines, which the RA and the final beneficiaries will follow, refer to Chapter 5 of the implementing rules, and will be absolutely followed by the competent unit of the Responsible Authority (Unit 4).

The Monitoring Committee will, among other duties, supervise the implementation of the visibility obligations, according to articles 31-35 of the implementing rules.

In addition, the Responsible Authority already has experience from the application of Community programmes which have been and which are being implemented under which it was/is the grant recipient.

3.1.1.7. Complementarity with similar actions financed by other EC instruments, if appropriate (Pertinent for all proposed actions in the Annual Programme 2010)

All the objectives described under the priorities that are planned to be implemented under the Fund, follow on from national actions taken for the same reasons at central, regional and local level.

The actions to be implemented complement and follow on from actions taken under the national ordinary budget of the Hellenic Police as well as under Community Programmes which have been and are being implemented under the European Refugee Fund II, regarding the implementation of voluntary returns. The knowledge and experience gained from implementing operational programmes under the 3rd Community Support Framework, INTERREG II and III, EQUAL and ARGO were also applied. Particular attention was paid when drafting the multiannual programme to the results of the implemented actions in the framework of the Community Initiative EQUAL and of the joint European operations, programmed and coordinated by Frontex, in the field of the integrated return management.

Specifically, via the Community Initiative EQUAL has been financed the printing of handy booklets in six (6) languages, which describe the process of asylum and the applicant asylum’s rights.

The preparation and the finalisation of the booklets’ text in the applicant asylum’s basic languages (Greek, English, French, Turkish, Iranian, Arabic), have been drafted with the collaboration of the Hellenic Police and the UNHCR.

These booklets were printed out by the Printing-house of the Hellenic Police in 75.000 copies and were distributed in the Services of the Hellenic Police in order to be covered the needs of the particular target group (asylum seekers).

Hellenic Police Headquarters has also been implementing various projects co-financed from operational programmes under the 2nd and 3rd Community Support Frameworks since 1995 and particular attention was therefore paid when preparing the multiannual and annual programmes to applying the knowledge and experience gained in order to include the best practices developed when planning the programmes.

As such, and given that the application of the provisions of the European Return Fund depends on cohesion with projects defined mainly in Objectives of the European Social Fund, the strategy developed within the framework of the European Return Fund is compatible with the objectives of the European Union Structural Funds (mainly of the European Social Fund), being pursued through sectoral and regional operational programmes in the 2008-2013 financial period.

For action 3.3.2., the draft annual programme is also in complementarity to the voluntary return actions implemented under the European Refugee Fund II which aimed at the establishment of effective mechanism for voluntary returns of failed asylum seekers and refugees.

In addition, to the above mentioned elements , for drafting the multiannual program and the annual programme, Greece took into account the general axes of the approved programs for the Structural Funds to be implemented during the period  2008-2013.

3.1.1.8. Financial Information

This specific project, which comes under priority 1, will receive 75% financing from Community resources (EURO 800.000,00) and 25 % from national resources (EURO 266.666,67 from the state budget), bringing public spending on this project to EURO 1.066.666,67. The national contribution must be covered by the Ministry of Citizen Protection, in cooperation with the Ministries of Finance and of Economy, Competitiveness and Mercantile Marine through the Public Investment Programme (and hence the ordinary budget) and the procedure, which will be followed for the implementation of the specific action according to our national legislation and the article 11 of the implementing rules.

3.1.2. Reinforcement of the special office for the implementation of the readmission agreements (Objective 1 under priority 1 of the Multiannual Programme ( MAP))

3.1.2.1. Purpose and scope of the action

Our country, within the framework of an effective and complete management of returns, has signed re-admission agreements with third countries, such as Turkey and Albania. Purpose of the settings up and operation of a special re-admission office (R.A.O.) is the Monitoring of the Readmission Agreements regarding their observation and implementation by contracted countries selections of information and co-operation with the regional police authorities. The special re-admission office cooperates with the regional police authorities and selects data proving the country of origin or the country of transit. In case that an agreement has been signed either with the country of origin or the country of transit, the office informs the foreign authorities in order to start and facilitate the return procedure.

For a better cooperation and communication between the regional police authorities and the readmission office, a quicker selection of information and a reliable exchange of information, in the context of the implementation of readmission agreements, it is necessary to be equipped with modern and operational devices, as follows:

- 4 computers, PCs with the proper software

- 2 multi-machines (Scanners, printers, fax, and photocopiers

The above equipment will be allocated as follows:

R.A.O

- Hellenic Police Headquarters / Alliens’ Division

  - 2 computers

2 POLICE DIRECTORATES WITH 1 COMPUTER AND 1 MULTIMACHINE FOR EACH ONE, AS FOLLOWS:

- Police Directorate of Magnesia

- Police Directorate of Lasithi

The equipment purchased in the framework of the action will improve the efficiency and management of the returns towards third countries with which Greece has signed readmission agreements.

3.1.2.2. Expected grant recipients

The Responsible Authority will be the grant recipient of this action and will assign some of her obligations to the appropriate Divisions of the Hellenic Police Headquarters of the Ministry of Interior.

3.1.2.3. Where appropriate, justification regarding project(s) implemented directly by the responsible authority acting as an executing body

The Ministry of Interior (Finance Division at Hellenic Police Headquarters) may act as the executing body of projects co financed by the European Return Fund where the project comes under its exclusive authority as the national public body and cannot be allocated to another agency or authority. According to our national legislation [articles 8 and 15 of the Presidential Decree 14/2001 (Government Gazette I 12/31.01.2001)], the Ministry of Interior / Hellenic Police Headquarters / Finance Division and Aliens Division can implement the above-mentioned action.

3.1.2.4. Expected quantified results

The expected results from the development and implementation of the abovementioned action will be the monitoring, the facilitation and the quicker implementation of readmission agreements by the contracting counties, and a more effective co-operation between regional police authorities and R.A.O..

3.1.2.5. Indicators to be used

Output :  The number of purchased p.cs, multi machines and printers for the efficient communication between the regional services and the R.A.O..

Outcome: Increased ability of more efficient and quicker communication between the Central Service (Hellenic Police Headquarters – Readmission Agreements Office) and the Regional Services, for the implementation of the Readmission Agreements.

Impact:  Enhanced information exchange and cooperation between the R.A.O. (Hellenic Police Headquarters) and the competent Regional Services.

3.1.2.6. Visibility of EC funding

As described in point 6 of action 3.1.1. of Priority 1.

3.1.2.7. Complementarity with similar actions financed by other EC instruments, if appropriate

As described in point 7 of action 3.1.1. of Priority 1.

3.1.2.8. Financial Information

This specific project, which comes under priority 1, will receive 75% financing from Community resources (EURO 9.000,00) and 25 % from national resources (EURO 3.000,00 from the state budget), bringing public spending on this project to EURO 12.000,00. The national contribution must be covered by the Ministry of Citizen Protection, in cooperation with the Ministry of Finance and of Economy, Competitiveness and Mercantile Marine through the Public Investment Programme (and hence the ordinary budget) and the procedure, which will be followed for the implementation of the specific action according to our national legislation and the article 11 of the implementing rules.

3.1.3. The improvement of the provision of psychological support to potential returnees by employing social workers and psychologists

(Objective 1 under priority 1 of the MAP)

Year after year our country is facing increasing of migratory flows, in terms of entry and stay of illegal immigrants. After the arrest of illegal immigrants, they should be returned to their countries of origin or third country that will accept them. However, the Greek authorities are facing difficulties in the return process. Until the completion of the return of illegal immigrants are detained at specially organized areas. The increasing of illegal immigrants will increase the number of special areas and thereby will increase the number of employed social workers / psychologists in order to cover the support needs of illegal immigrants and to be completed the procedures to return quickly.

3.1.3.1. Purpose and scope of the action

The provision of psychological support to potential returnees as well as the information on the political and financial situation in the countries of origin will be carried out by social workers and psychologists. Their services are meant for:

- all arrested illegal immigrants,

- arrested illegal immigrants, who stay in special host places, until the legal status regarding their return is clarified  (e.g. political asylum application until its approval or its rejection) and

- vulnerable persons, such as minors, unaccompanied minors, disabled and elderly persons, pregnant women and persons who have suffered psychological, physical or sexual violence.

It is expected that 120 social workers and 120 psychologists will be engaged in this work (the allocation will be the same for both specialties) and they

- In Athens (Aliens Division of Attica)

- In Thessalonica (Aliens Division of Thessalonica)

- In the Orestiada Police Directorate

- In the Lesbos Police Directorate

- In the Samos Police Directorate

- In the Chios Police Directorate

- In the Dodecanese Police Directorate

- In the Achaia Police Directorate

This action implies a continuation of action included in annual programmes 2008 and 2009. The selection procedure, for the employment of the above-mentioned personnel, is in process and hasn’t been finished yet, for the annual programmes 2008 and 2009.

In addition, this action is also included in the Greek Action Plan on the management of migration flows presented by the Greek Government in August 2010. It is expected that the implementation of this action will significantly contribute to addressing the needs indentified in the Action Plan.

The implementation of the action under the 2010 AP will start after the approval of the 2010 Annual Program. Due to the national legal requirements, the recruitment process will be subject to a new selection procedure. The action will finish by 30-06-2012.

3.1.3.2. Expected grant recipients

The Responsible Authority will implement this action in association with the appropriate Divisions of the Hellenic Police Headquarters of the Ministry of Citizen Protection.

3.1.3.3. Where appropriate, justification regarding project(s) implemented directly by the responsible authority acting as an executing body

The Ministry of Citizen Protection (Finance Division of Hellenic Police Headquarters) may act as the executing body of projects co financed by the European Return Fund where the project comes under its exclusive authority as the national public body and cannot be allocated to another agency or authority. According to our national legislation [articles 8 and 15 of the Presidential Decree 14/2001 (Government Gazette I 12/31.01.2001)], the Ministry of Citizen Protection / Hellenic Police Headquarters / Finance Division, Aliens Division and Civil Personnel Division will implement the above-mentioned action.

3.1.3.4. Expected quantified results

The development and the materialization of the afore-mentioned action will contribute to the upgrading of the provided services by police authorities to arrested illegal immigrants, who are going to be sent back, and to the promotion of the respect for their human rights, in order that return procedures may be more effectively materialized.

3.1.3.5. Indicators to be used

Output: Number of social workers and psychologists.

Outcome: Upgrade of the provided services to the arrested illegal immigrants-returnees.  Better implementation of the obligations arising from the Directive of the European Parliament and the Council concerning common standards and procedures for returning illegally staying third country nationals.

Impact:   Development of the effective return management.

3.1.3.6. Visibility of EC funding

As described in point 6 of action 3.1.1. of Priority 1.

3.1.3.7. Complementarity with similar actions financed by other EC instruments, if appropriate

As described in point 7 of action 3.1.1. of Priority 1.

3.1.3.8. Financial Information

This specific project, which comes under priority 3, will receive 75% financing from Community resources (EURO 2.525.000,00) and 25 % from national resources (EURO 841.666,67 from the state budget), bringing public spending on this project to EURO 3.366.666,67. The national contribution must be covered by the Ministry of Citizen Protection, in cooperation with the Ministries of Finance and of Economy, Competitiveness and Mercantile Marine through the Public Investment Programme (and hence the ordinary budget) and the procedure, which will be followed for the implementation of the specific action according to our national legislation and the article 11 of the implementing rules.

3.1.4. Bilateral meetings with migration authorities of the partner third countries (Objective 2 under priority 1 of the MAP)

3.1.4.1. Purpose and scope of the action

In many cases the immediate materialization of return decisions gets delayed, having as a consequence the long detention of illegal immigrants under return and the possible cancellation of their return to their countries of origin or to another country, where they get accepted, on the basis of readmission agreements.

The above problems are mainly due to the lack of cooperation on the part of some countries’ Consular Authorities. Namely, many times Consular Authorities delay the issuance of travel documents for their nationals under return. This situation in connection with the inability of Consular Authorities to identify the illegal immigrants as nationals of the country in question, obstructs the work of the competent Hellenic Police Services.

Moreover, some countries (e.g. Turkey), which have signed readmission agreements, do not enforce them.  Also, a large number of illegal immigrants come from third countries of Asia (e.g. Afghanistan and Pakistan) and from African countries (e.g. Somalia and Nigeria), with which readmission agreements have not been signed, a fact that creates problems regarding the return of their nationals.

The bilateral meetings between Greek experts and corresponding experts from third countries aim at:

- The more effective enforcement of readmission agreements,

- The signing of readmission agreements with countries, which present large outflow of illegal immigrants,

- The amelioration of the cooperation with the Consular Authorities, with the view of having their nationals’ (illegal immigrants)  travel documents issued in time.

For 2010, it is proposed to be financing a bilateral meeting in Turkey with the participation of 5 experts from the Aliens Division / Hellenic Police Headquarters, for the purpose of considering the possibility of the signature of a new readmission agreement with this country due to increasing number of illegal migrants coming from this country and the delays in issuing travel documents.

This action implies a continuation of action included in annual programmes 2008 and 2009 and will starts after the approval of the 2010 Annual Program and will finish the 30-06-2012.

3.1.4.2. Expected grant recipients

The Responsible Authority will implement this action in association with the appropriate Divisions of the Hellenic Police Headquarters of the Ministry of Citizen Protection.

3.1.4.3. Where appropriate, justification regarding project(s) implemented directly by the responsible authority acting as an executing body

The Ministry of Citizen Protection (Finance Division at Hellenic Police Headquarters) may act as the executing body of projects co financed by the European Return Fund where the project comes under its exclusive authority as the national public body and cannot be allocated to another agency or authority. According to our national legislation [articles 8 and 15 of the Presidential Decree 14/2001 (Government Gazette I 12/31.01.2001)], the Ministry of Citizen Protection / Hellenic Police Headquarters / Finance Division and Aliens Division will implement the above-mentioned action.

3.1.4.4. Expected quantified results

The expected results from the development and the implementation of the afore-mentioned action may be the following:

- the effective implementation of return decisions due to means of signing readmission agreements,

- the achievement of a more effective cooperation with the Consular Authorities, which are responsible for the timely issuance of travel documents for their nationals, who are illegal immigrants,

- the signing of readmission agreements with new countries.

3.1.4.5. Indicators to be used

Output: Number of immigration services or other competent, for the readmission agreements, services with which communication channels and working methods have not been established. Number of immigration services or other services competent for the readmission agreements with which cooperation is deepened and strengthened.

Outcome: Improved quality of service. Strengthened cooperation with third country consular, immigration or other services competent, for the readmission agreements, .

Impact:   More effective return policy, enhanced credibility of migration policy, reduced costs of return.

3.1.4.6. Visibility of EC funding

As described in point 6 of action 3.1.1. of Priority 1.

3.1.4.7. Complementarity with similar actions financed by other EC instruments, if appropriate

As described in point 7 of action 3.1.1. of Priority 1.

3.1.4.8. Financial Information

This specific project, which comes under priority 3, will receive 75% financing from Community resources (EURO 10.000,00) and 25 % from national resources (EURO 3.333,33 from the state budget), bringing public spending on this project to EURO 13.333,33. The national contribution must be covered by the Ministry of Citizen Protection, in cooperation with the Ministry of Finance and of Economy, Competitiveness and Mercantile Marine through the Public Investment Programme (and hence the ordinary budget) and the procedure, which will be followed for the implementation of the specific action according to our national legislation and the article 11 of the implementing rules.

3.1.5. Bilateral meetings with the Consular Authorities of the third countries (Objective 2 under priority 1 of the  MAP)

3.1.5.1. Purpose and scope of the action

A large number of illegal immigrants, coming from countries such as Somalia, Afghanistan and Bangladesh, enter our country. During the return procedure regarding arrested illegal immigrants, many problems arise, which may significantly delay or even, in some cases, cancel the return to the country of origin, for the following reasons:

- The lack of consular representation by some countries (e.g. Afghanistan, Somalia and Bangladesh) in Greece;

- Non-recognition of the travel documents of the arrested immigrants, as nationals of the aforementioned countries;

- Long delays in the issuance of travel documents for immigrants from the aforementioned countries who should be returned.

In order to deal with this situation and the problems arising during the return procedure, new methods of cooperation with the consular authorities of the countries that are not represented in Greece will be developed. To this purpose, bilateral meetings with consular representatives of the countries that are not represented in Greece but are based in other countries will be held in Greece. The objective is to verify the nationality of illegal immigrants from the aforementioned countries who should be returned and to proceed to the immediate issuance of their travel documents.

More specifically, twelve (12) five-day bilateral meetings with the Consul and two representatives of the following consular authorities will be held in Greece:

- The consular authority of Afghanistan in Brussels (4 meetings per year),

- The consular authority of Bangladesh in Rome (4 meetings per year),

- Officials from Somalia (4 meetings per year).

This action implies a continuation of action included in annual programme 2008 and 2009 and will starts after the approval of the 2010 Annual Program and will finish the 30-06-2012. Under the 2008 annual program, there were two meetings held in Athens with representatives of the Embassy of Afghanistan based in Brussels since Afghanistan is not represented by consular authorities in Greece. These meetings were held in order to identify the nationality of illegal immigrants whose should return to their countries of origin and the immediate issue of travel documents. The action under the 2009 annual programme is underway.

3.1.5.2. Expected grant recipients

The Responsible Authority will implement this action in association with the appropriate Divisions of the Hellenic Police Headquarters of the Ministry of Citizen Protection.

3.1.5.3. Where appropriate, justification regarding project(s) implemented directly by the responsible authority acting as an executing body

The Ministry of Citizen Protection (Finance Division at Hellenic Police Headquarters) may act as the executing body of projects co financed by the European Return Fund where the project comes under its exclusive authority as the national public body and cannot be allocated to another agency or authority. According to our national legislation [articles 8 and 15 of the Presidential Decree 14/2001 (Government Gazette I 12/31.01.2001)], the Ministry of Citizen Protection  / Hellenic Police Headquarters / Finance Division and Aliens Division will implement the above-mentioned action.

3.1.5.4. Expected quantified results

The expected results of the development and implementation of the aforementioned action are the following:

- the development of new methods of cooperation with consular authorities not represented in Greece;

- the establishment of a more efficient cooperation with consular authorities as regards the timely issuance of travel documents for their nationals who are illegal immigrants;

- the reduction in detention time for illegal immigrants and the acceleration of their return to their countries of origin.

3.1.5.5. Indicators to be used

Output: Number of consular services with which communication channels and working methods are established, number of consular services with which cooperation is deepened and strengthened.

Outcome: Improved quality of service, strengthened cooperation with third country consular services.

Impact:  More efficient return policy, enhanced credibility of migration policy, reduced costs of return.

3.1.5.6. Visibility of EC funding

As described in point 6 of action 3.1.1. of Priority 1.

3.1.5.7. Complementarity with similar actions financed by other EC instruments, if appropriate

As described in point 7 of action 3.1.1. of Priority 1.

3.1.5.8. Financial Information

This specific project, which comes under priority 3, will receive 75% financing from Community resources (EURO 100.000,00) and 25 % from national resources (EURO 33.333,33 from the state budget), bringing public spending on this project to EURO 133.333,33. The national contribution must be covered by the Ministry of Citizen Protection, in cooperation with the Ministries of Finance and of Economy, Competitiveness and Mercantile Marine  through the Public Investment Programme (and hence the ordinary budget) and the procedure, which will be followed for the implementation of the specific action according to our national legislation and the article 11 of the implementing rules.

3.1.6. Enforced/assisted returns of third-country nationals who do not or no longer fulfill the conditions for entry and stay (Objective 3 under priority 1 of the MAP)

3.1.6.1. Purpose and scope of the action

Nationals of third countries who do not meet the conditions for their stay in the Greek territory or their presence pose direct threat against the public order or the national security or their removal is ordered after a decision taken by Administrative or Judicial authorities, they are compulsorily removal from the national territory, observing in any case the rules provided for in the international conventions.

The removal of persons who do not cause specific problems is carried out voluntarily without an escort, by road, by air (regular flights) or by sea.

The financial aspects of the above actions will cover expenditures relating to the implementation of enforced/ assisted returns, such as the issuance of travel documents, the purchase of tickets or chartering of planes, the accommodation and food for returnees during the return operations as well as the expenditures related to police escorts accompanying the returnees during the return operations (tickets, food and accommodation in the third country).

However, there are special cases which need special management by the services responsible for their return, since during the process of the forced returns several problems arise impeding the returns and finally, leading to their annulment.

Such cases are:

- Non – existence of communal or bilateral re-admission agreements with third countries such as Iraq, Afghanistan, e.t.c. causing serious problem in co-operation in the field of returns.

- The illegal aliens who cause problems during the return process to their countries and their removal is to be carried out by air with police escort.

- Lack of co-operation with consulates of some states in our country, which do not issue travel documents or do not show the necessary interest for co-operation in order to issue the necessary travel documents within a reasonable time.

- Lack of direct air connections with countries of origin of illegal immigrations.

As a result of the above, the immigrants under return are   detained for a long period and, finally, the return is cancelled in some cases.

Our country, in order to solve the above problems and carry out the scheduled returns will hold flights by hiring aircrafts also for countries which have not signed re-admission agreements in order to increase the execution rates of the issued return decisions.

For 2010, it is scheduled to carry out about ten (10) flights with hired aircrafts, so that the illegal immigrants to be transported to their countries of origin, mainly Egypt, Pakistan and Iraq, eventually to other countries.This action is limited to the forced returns.

This action implies a continuation of action included in annual programmes 2008 and 2009 and will starts after the approval of the 2010 Annual Program, with a new selection procedure and will finish the 30-06-2012.

Under the 2008 AP, five (5) charter flights have been implemented and many individual forced returns of illegal immigrants to third countries with or without the police escort took place. The implementation of the 2009 annual programme is in progress.

3.1.6.2. Expected grant recipients

The Responsible Authority will implement this action in association with the appropriate Divisions of the Hellenic Police Headquarters of the Ministry of Citizen Protection.

3.1.6.3. Where appropriate, justification regarding project(s) implemented directly by the responsible authority acting as an executing body

The Ministry of Citizen Protection (Finance Division at Hellenic Police Headquarters) may act as the executing body of projects co financed by the European Return Fund where the project comes under its exclusive authority as the national public body and cannot be allocated to another agency or authority. According to our national legislation [articles 8 and 15 of the Presidential Decree 14/2001 (Government Gazette I 12/31.01.2001)], the Ministry of Citizen Protection / Hellenic Police Headquarters / Finance Division and Aliens Division will implement the above-mentioned action.

3.1.6.4. Expected quantified results

The expected results from the development – implementation of the said action, according to its description, will be the following:

- Increase of the rates of the illegal immigrants who return to their countries of origin and decrease of the illegal immigrants in our country and, by extension, in the E.U. countries.

- Return of illegal immigrants in the countries of origin with which there are not direct air connections.

- Reduction of expenses spent for the return of illegal immigrants and their escorts, due to the decrease of their detention period and the less number of escorts who will be needed in relation to the solely escorted return.

3.1.6.5. Indicators to be used

Output: Number of enforced returns simplified and implemented.

Outcome: Enhanced credibility and integrity of immigration policies. Reduced custody period of persons waiting for forced removal.

Impact: More efficient return policy.

3.1.6.6. Visibility of EC funding

As described in point 6 of action 3.1.1. of Priority 1.

3.1.6.7. Complementarity with similar actions financed by other EC instruments, if appropriate

As described in point 7 of action 3.1.1. of Priority 1.

3.1.6.8. Financial Information

This specific project, which comes under priority 1, will receive 75% financing from Community resources  (EURO 5.076.934,40) and 25 % from national resources (EURO 1.692.311,47 from the state budget), bringing public spending on this project to EURO 6.769.245,87. The national contribution must be covered by the Ministry of Citizen Protection, in cooperation with the Ministries of Finance and of Economy, Competitiveness and Mercantile Marine through the Public Investment Programme (and hence the ordinary budget) and the procedure for the implementation of the specific action, will be followed according to our national legislation and the article 11 of the implementing rules.

3.1.7 Upgrading of the Deportation Department of Attica Aliens Division

(Objective 3 under priority 1 of the MAP)

3.1.7.1. Purpose and scope of the action

In our country, immigration problem and the simultaneous development of actions by the Hellenic Police, financed by European funds leads to higher requirements in human resources, better technology, computer equipment and other relevant services.

The Aliens Division Department deals with treatment of migratory flows in terms of entry and stay of illegal immigrants coming from third countries and consequently the implementation of compulsory returns of illegal immigrants.

Given the proximity to the International Athens Airport, the Department of Deportation of the Aliens Division of Attica plays a central role in the management of returns in Greece. The Department holds the responsibility for carrying out the returns of illegal immigrants from Greece who were apprehended both in Attica and other Police Divisions in the whole country.

This Department manages daily a huge number of illegal migrants and returnees and in particular is in charge of the following procedures/activities:

- recording and control of any earlier decisions,

- further examination of it (referred to municipalities, judicial authorities etc.) and then proposing a deportation decision

- custody - expulsion - entry extensions beyond the six months period,

- registration and examination of any asylum claims,

- transfer of detained immigrants to the respective Consulates for the recognition and the issuing of travel documents,

- flight planning to return to their origin country,

- transfer of detained immigrants to the airport escorts by the policemen of Deportation Department.

Furthermore, it is worth adding that the number of illegal immigrants being effectively returned has risen sharply. For example, the 2006 average per month was 700 and in 2010 is about 3000.

So, for faster and effective implementation of all return procedures need better organization of the department and the following equipment:

- 35 P.Cs with appropriate software because the existing electronic devices have gained 10 years ago and the daily use have begun to exhibit serious technical problems

- 1 server with UPS

- 4 Laptops

- 16 multi machines (Laser printers, fax ,scanner etc).

- 20 Digital Cameras that will help identify the illegal immigrants

- 10 telephone machines.

- 6 police vehicles

The installation of new equipment will reduce the delays in processing the documentation related to the return (notably the procurement of indispensable travel documents) and consequently should reduce the period of custody of persons waiting for removal. The new equipment will also enhance the integrity and credibility of the process (since storing of information in one place and communicating it quickly should reduce the risk of error or miscommunication between different departments as well as international partners). In particular, better communication and cooperation between the Aliens Division of the HPHQ and other relevant Departments of  Immigration in Athens and in the whole country would be improved. It should also enable better cooperation and communication with consular authorities and immigration services of third countries, since the new equipment (e.g., multimachines, digital cameras and telephones) should enable swifter and more comprehensive exchange of information and enable to obtain travel documents more easily.

This action is new and will begin after approval of the 2010 annual program and will be finished until 30-06-2010.

3.1.7.2. Expected grant recipients

The Responsible Authority will implement this action in association with the appropriate Divisions of the Hellenic Police Headquarters of the Ministry of Citizen Protection.

3.1.7.3. Where appropriate, justification regarding project(s) implemented directly by the responsible authority acting as an executing body

The Ministry of Citizen protection (Finance Division at Hellenic Police Headquarters) may act as the executing body of projects co financed by the European Return Fund where the project comes under its exclusive authority as the national public body and cannot be allocated to another agency or authority. According to our national legislation [articles 8 and 15 of the Presidential Decree 14/2001 (Government Gazette I 12/31.01.2001)], the Ministry of Citizen Protection / Hellenic Police Headquarters / Finance Division and Aliens Division will implement the above-mentioned action.

3.1.7.4. Expected quantified results

The expected results from the development and implementation of the abovementioned action are:

- Faster processing of extradition procedures

- The significant increase in the number of forced returns and reducing the time spent in places of detention for illegal immigrants.

3.1.7.5. Indicators to be used

Output: The number of purchased p.cs, multi machines and printers , communication equipment for the efficient and faster communication between the regional services and divisions.

Outcome: Improving the organization and operation of the service

Impact: Improving the organization and operation of the service between Aliens Division of the HPHQ and the regional services and divisions and increasing the number of returnees to their home countries.

3.1.7.6.. Visibility of EC funding

As described in point 6 of action 3.1.1. of Priority 1.

3.1.7.7. Complementarity with similar actions financed by other EC instruments, if appropriate

As described in point 7 of action 3.1.1. of Priority 1.

3.1.7.8. Financial Information

This specific project, which comes under priority 2, will receive 75% financing from Community resources (EURO 187.500,00) and 25 % from national resources (EURO 62.500,00 from the state budget), bringing public spending on this project to EURO 250.000,00. The national contribution must be covered by the Ministry of Citizen Protection, in cooperation with the Ministry of Finance and of Economy, Competitiveness and Mercantile Marine through the Public Investment Programme (and hence the ordinary budget) and the procedure for the implementation of the specific action, will be followed according to our national legislation and the article 11 of the implementing rules.

3.1.8. Creation of pre-removal detention centre for third-country nationals who are under the procedure of return in Amigdaleza of Attica (Objective 3 under priority 1 of the MAP)

3.1.8.1. Purpose and scope of the action

The objective of this action is to expand the available capacity of pre-removal detention centers by establishing a new pre-removal detention center for third-country nationals who are under the procedure of return in Amigdaleza, Attica region.

According to Law 3907 of 26.1.2011, migrants who are issued with a return decision following the screening process, are oriented towards pre-removal detention centers in view of organizing their return. With the significant flow of irregular migrants to Greece, the population of potential returnees has been also growing steadily. However, the capacity to detain illegal migrants during the return process has not risen to match these needs. Existing pre-removal detention centers are already overburdened and overpopulated. The limited detention capacity represents one of the main bottlenecks preventing the increase of the number of returns. In that context, there is urgent need to increase detention capacity, especially in the Attica region. The establishment of the Amigdaleza center will represent a first step in this process.

The objective of this project is fully aligned with the Greek Action Plan on Management of Migration Flows and in light of the recommendations presented in the 2011 report of the Fundamental Rights Agency.

The operation of the center would comply with EU standards, in particular, the requirements of the Return directive, notably art. 15 to 17, will be fully respected. The material conditions in the center will also represent an improvement in comparison with the other existing pre-removal centers. Within the center, special spaces will be established in order to allow access of NGOs and lawyers to detainees.

The specific center will be used, only, as a pre-removal-detention center, for hosting the immigrants who illegally entered the Hellenic territory and have been issued with return decisions, therefore, no asylum seekers will be hosted in the center. However, the Greek authorities will ensure the full respect for asylum procedures.

The center expenditures concern the operation of totally 260 existing containers. The 208 of them, divided in 13 wings, will be used for the host of over 800 apprehended illegal immigrants and the rest for administrative purposes (Command Centers, medical centers, meeting spaces for NGOs and lawyers etc.). Until June 2012, only 52 containers were renovated with the capacity up to to 208 people. This part of renovation costs will be charged to the 2010 AP. This category of costs will encompass refurbishment works-modifications of the existing containers’ infrastructure (i.e. doors, iron staircases, plumbing and electrical equipment, Guards’ kiosks etc.). The 2010 AP will also cover electrical and electronic equipment and furniture (white electrical devices, air conditions etc.), security and safety equipment (signs, lighting projectors etc.), Household items (beds, blankets etc.) and cleaning equipment (litter bins etc.), administrative equipment (pcs, printers etc.)

In addition, the operational costs and running costs of detention centers, including consumables for returnees will also be covered under this action aiming to the improvement of the living standards of the returnees. This category of costs will approximately amount to 250 000 euro a month assuming the center would be used in its full capacity  hosting 800 persons . The indicative list of this cost  category includes maintenance of the centre, hygiene kits for the immigrants, (toothbrushes toothpaste, soaps etc.), sheets, operational costs - consumables of the centre, disinfection, pharmaceutical material, cconsumables for the operation of laundries, feeding, cleanliness, outdoor cleaning of the centre, crane rental fee (moving of containers).

3.1.8.2. Expected grant recipients

The Responsible Authority will implement this action in association with the appropriate Divisions of the Hellenic Police Headquarters of the Ministry of Citizen Protection.

3.1.8.3. Where appropriate, justification regarding project(s) implemented directly by the responsible authority acting as an executing body

The Ministry of Citizen Protection (Finance Division at Hellenic Police Headquarters) may act as the executing body of projects co financed by the European Return Fund where the project comes under its exclusive authority as the national public body and cannot be allocated to another agency or authority. According to our national legislation [articles 8 and 15 of the Presidential Decree 14/2001 (Government Gazette I 12/31.01.2001)], the Ministry of Citizen Protection / Hellenic Police Headquarters / Finance Division and Aliens Division will implement the above-mentioned action.

3.1.8.4. Expected quantified results

The expected results from the development – implementation of the said action, according to its description, will be the following:

•	Improve the detention conditions of the illegal immigrants who return to their countries of origin in accordance to the international conventions.

•	Separate third-country nationals from ordinary prisoners.

•	Create adequate separate accommodation guaranteeing adequate privacy.

3.1.8.5. Indicators to be used

Output: increased detention capacity in Attica region (number of places), number of returnees hosted.

Outcome: Improve the detention conditions of the illegal immigrants, increase the number  returns

Impact: More efficient return policy in accordance to the international conventions.

3.1.8.6. Visibility of EC funding

As described in point 6 of action 3.1.1. of Priority 1.

3.1.8.7. Complementarily with similar actions financed by other EC instruments, if appropriate

As described in point 7 of action 3.1.1. of Priority 1.

3.1.8.8. Financial Information

This specific project, which comes under priority 1, will receive 75% financing from Community resources (EURO 675.000,00) and 25 % from national resources (EURO 225.000,00 from the state budget), bringing public spending on this project to EURO 900.000,00. The national contribution must be covered by the Ministry of Citizen Protection, in cooperation with the Ministries of Finance and of Development, Competitiveness and Shipping through the Public Investment Programme (and hence the ordinary budget) and the procedure for the implementation of the specific action, will be followed according to our national legislation and the article 11 of the implementing rules.

  - ACTIONS IMPLEMENTING PRIORITY 2

The implementation of joint flights with other EU Member States (Objective 1 under priority 2 of the MAP)

3.2.1.1. Purpose and scope of the action

For the development and the implementation of an integrated return management, Greece will seek to enhance the cooperation on returns with the competent authorities of other Member States through implementation of joint flights, either via FRONTEX or bilaterally.

The implementation of joint flights with other EU Member States aims at pooling the different skills, experiences and resources of the Member States’ Authorities involved in implementing joint flights.

In the framework of this action for 2010, Greece will implement three (3) joint flights to Pakistan in collaboration with Cyprus, and one (1) joint flight to Nigeria in collaboration with Germany. Each flight will return approximately fifty (50) escorted or not returnees from Greece and a respective number of returnees from the other Member State.

This action will start after the approval of the 2010 Annual Program and finishing the 30-06-2012.

The action is a continuation of the similar action under the 2009 annual programme. Under the 2009 AP, two preparatory meetings took place between representatives of Cyprus and Greece to discuss issues relating to the implementation of joint operations. The joint flight to Nigeria is currently being scheduled.

3.2.1.2. Expected grant recipients

The Responsible Authority will implement this action in association with the appropriate Divisions of the Hellenic Police Headquarters of the Ministry of Citizen Protection.

3.2.1.3. Where appropriate, justification regarding project(s) implemented directly by the responsible authority acting as an executing body

The Ministry of Citizen protection (Finance Division at Hellenic Police Headquarters) may act as the executing body of projects co financed by the European Return Fund where the project comes under its exclusive authority as the national public body and cannot be allocated to another agency or authority. According to our national legislation [articles 8 and 15 of the Presidential Decree 14/2001 (Government Gazette I 12/31.01.2001)], the Ministry of Citizen Protection / Hellenic Police Headquarters / Finance Division and Aliens Division will implement the above-mentioned action.

3.2.1.4. Expected quantified results

The expected results from the development – implementation of the said action, according to its description, will be the following:

- The implementation of returns, to countries which are not accessible with regular flights from our country and present difficulties.

- The achievement of an integrated return management.

- The exchange of best practices with the competent services of the other EU Member States.

- The reduction of the enforced or assisted returns’ expenses.

- More efficient return procedures.

3.2.1.5. Indicators to be used

Output: Number and type of joint integrated return plans developed. Types of resources, skills and experiences pooled.

Outcome: Number of immigrants returned in the context of joint return plans. Improved co-ordination and efficiency in EU return policies.

Impact: Enhanced administrative capacity of MS in return policies. Reduced cost at EU level and increased cost efficiency of return policies.

3.2.1.6. Visibility of EC funding

As described in point 6 of action 3.1.1. of Priority 1.

3.2.1.7. Complementarity with similar actions financed by other EC instruments, if appropriate

As described in point 7 of action 3.1.1. of Priority 1.

3.2.1.8. Financial Information

This specific project, which comes under priority 2, will receive 75% financing from Community resources (EURO 300.000,00) and 25 % from national resources (EURO 100.000,00 from the state budget), bringing public spending on this project to EURO 400.000,00. The national contribution must be covered by the Ministry of Citizen Protection, in cooperation with the Ministry of Finance and of Economy, Competitiveness and Mercantile Marine through the Public Investment Programme (and hence the ordinary budget) and the procedure for the implementation of the specific action, will be followed according to our national legislation and the article 11 of the implementing rules.

3.3 	ACTIONS IMPLEMENTING PRIORITY 3

3.3.1. The implementation of voluntary returns including reintegration measures (Objective 1 under priority 3 of the  MAP)

3.3.1.1. Purpose and scope of the action

The implementation of the above mentioned action includes four main stages, which are necessary for the integration of the action and the success of the expected results:

- Stage 1: Information campaigns on the possibilities of voluntary returns for the target groups. The campaigns will be carried out by means of brochures, posters and radio spots. Posters and brochures will be printed in the most common languages spoken by immigrants residing in Greece. The posters and the brochures will be distributed largely in public places and services and NGOs. The messages in these languages will be broadcasted by the state radio and/or private radio stations. In addition, information actions will be carried out locally in regions with larger populations of third country nationals.

- Stage 2: Re-integration measures before or after the return to the country of origin.  This stage includes optional participation in a re-integration program, which will facilitate the stay in their countries of origin and the kind of the above measures, like as household supplies-technical training-installation first steps e.t.c., will be described in detail in the call for proposals.

- Stage 3: Preparation and implementation of voluntary return operations. This stage includes measures relevant for the preparation and implementation of voluntary returns such as the issuance of travel documents, where needed, the ticketing, escorting to the airport, rendering of services at the transit airports, when there is no direct flight, and transfer to another plane for the final destination. It is expected that approximately between two thousand and three thousands (2000-3000) immigrants will be voluntarily returned to their countries of origin.

- Stage 4: Reception in the country of origin. This stage includes the reception of the returnees in their countries of origin and the provision of a small re-integration allowance.

The call for proposals will be prepared and launched after the approval of the 2010 annual program.

This action implies a continuation of action included in annual programme 2009 and will starts after the approval of the 2010 Annual Program and finishing the 30-06-2012 and will be implemented through the call for proposals procedure..

In the framework of the 2009 annual programme, it is expected that around 900 voluntary returns would be implemented. Till October 2010, approximately 270 persons have been returned. The information campaign has been launched in summer 2010 with TV spots, information in newspapers and meetings addressed to potential returnees.

In addition, this action is also included in the Greek Action Plan on the management of migration flows presented by the Greek Government in August 2010. It is expected that the implementation of this action will significantly contribute to addressing the needs indentified in the Action Plan.

3.3.1.2. Expected grant recipients

The expected grant recipients will be NGOs or international organisations capable to implement the action.

3.3.1.3. Where appropriate, justification regarding project(s) implemented directly by the responsible authority acting as an executing body

n/a

3.3.1.4. Expected quantified results

The expected results of the development and implementation of the aforementioned action are the following:

- information campaign on voluntary return possibilities among the larger population and individual counseling to those interested to return in their countries of origin,

- the implementation of voluntary return operations (logistical preparation of the operation, transport to the countries of origin etc.) and

- the short term support measures aiming at the re-integration of returnees.

- the increased number of the voluntarily returnees, in relation to the forced returns.

3.3.1.5. Indicators to be used

Output: Number of voluntary returns implemented, number of persons voluntary returned.

Outcome: Increased effectiveness and sustainability of returns.

Impact: More effective return policy.

3.3.1.6. Visibility of EC funding

In action that R.A.  acts as an awarding body in the relevant article of Grant Agreement sets out the obligations of the final beneficiaries regarding their responsibilities of  information and publicity in accordance with E (2008) 796 Decision of the European Commission which is binding:

(a) accept to be included in the list of Final Beneficiaries which is posted on the website of the Fund and where there will be reference to the name of the Final Beneficiary, the title of the Action and the amount of the funding allocated for the implementation of the Action

(b) follow publicity requirements as per article 34 of the said Decision.

Specifically, the Final Beneficiary shall:

(i) place a permanent sizable sign in a visible area at the latest three months after the completion of the Action provided that the total community contribution exceeds the 100.000 Euros and refers to amount given for assets purchase. The sign makes reference to the type and name of the Action.

As the Action is financed in the framework of the Annual Program that is co-funded by the Fund, the Final Beneficiary ensures that the participants in the activity have been informed on the funding.

In each document, including certificates of participation or other certificates, as far as this Action is concerned, it is mentioned that the project is co-funded by the Fund.

(ii) The information and explanatory signs will specifically have:

- the logo of the European Union and reference to the European Union according to Regulation 2008/796/EC (Annex 10)

- the Fund and its logo

- the  title of Action and the  total budget ( co-funded at 75% by European Fund and at 25% by National Funds).

3.3.1.7. Complementarity with similar actions financed by other EC instruments, if appropriate

As described in point 7 of action 3.1.1. of Priority 1.

3.3.1.8. Financial Information

This specific project, which comes under priority 3, will receive 75% financing from Community resources (EURO 3.750.000,00) and 25 % from national resources (EURO 1.250.000,00 from the state budget), bringing public spending on this project to EURO 5.000.000,00. The national contribution must be covered by the Ministry of Citizen Protection, in cooperation with the Ministries of Finance and of Economy, Competitiveness and mercantile Marine through the Public Investment Programme (and hence the ordinary budget) and the procedure for the implementation of the specific action, will be followed according to our national legislation and the article 11 of the implementing rules.

3.4	ACTIONS IMPLEMENTING PRIORITY 4

3.4.1. Trainings of the Hellenic Police personnel (Objective 1 under priority 4 of the  MAP)

3.4.1.1. Purpose and scope of the action

The training and the information of police personnel in all regional services on issues regarding the management of illegal immigrants’ returns are deemed necessary. The key to successful returns is to hold seminars and implement practices of common training for police personnel as regards the legal and practical aspects of return operations for arrested aliens to be returned.

This action includes the following trainings:

- Trainings on return procedures of the illegal immigrants.

These trainings aim at the training and the continuous education of police personnel from all regional services on issues regarding the procedure of return of illegal immigrants arrested in our country. The trainings will cover the whole return procedure, from the issuance of the return decision to the accomplishment of the return of the illegal immigrant to his/her country of origin and will be in line with national and community law.

A two-day training 200 persons (in Athens (120) and Veria (80) persons) from various co-competent police authorities has been scheduled for 2010.

- Trainings on escorted return procedures of the arrested illegal immigrants.

The aforementioned trainings aim at:

- The training and information of police personnel on issues regarding escorted return procedures;

- The dealing with and the remedy of problems arising during the return procedure;

- The modernization of methods and practices used during the return procedure.

A two-day training in Athens for 50 persons from various co-competent police authorities has been scheduled for 2010.

- Trainings on readmission procedures

The mentioned training aims at training the police personnel involved in the implementation of the readmission agreements. More specifically, information and training will be provided on the existing agreements, the problems arising during their implementation and the ways of resolving them, while at the same time training will be provided on the implementation of efficient practices for their realization.

For the year 2010, 60 persons from various co-competent police authorities will be trained in Athens in a two-day course.

- Training on the issues related to the protection of potential returnees' human rights

The training of police personnel on guaranteeing and respecting the human rights of the immigrants in detention is of highest importance. On the one hand, our country will be harmonized with the Community legislation, on the other hand the established right of each person and more specifically of the immigrants in detention as to the safeguarding and protection of their rights will be guaranteed. These training courses will provide for the information of the police personnel in charge of guarding the arrested persons and the illegal immigrants to be returned, on issues of their obligations arising from national and community legislation.

For the year 2010, a two-day training of 250 persons from various co-competent police authorities in Athens, Veria, Patras, Ioannina and Alexandroupoli has been scheduled.

- Trainings on the treatment of vulnerable potential returnees

The specific training aims at the best possible treatment of the vulnerable groups as for example elderly people, pregnant women, disabled persons, etc. by guaranteeing and protecting their human rights at the same time.

The a-m problems are foreseen to be accomplished through trainings which will improve and modernize the existing methods concerning the treatment of the vulnerable groups.

For the year 2010, the training of 240 persons from various co-competent police authorities in Athens, Veria, Alexandroupoli, Dodecanese, Samos and Lesvos will be provided in a two-day course.

This action implies a continuation of action included in annual programme 2008 and 2009  and will starts after the approval of the 2010 Annual Program and will finish the 30-06-2012.

However, the trainees will not be the same, among the A.P. 2009 and 2010.

The procedure for the implementation of the above mentioned action for the annual programme 2009 is ongoing and has not been yet finished,

3.4.1.2. Expected grant recipients

The Responsible Authority will implement this action in association with to the appropriate Divisions of the Hellenic Police Headquarters of the Ministry of Citizen Protection.

3.4.1.3. Where appropriate, justification regarding project(s) implemented directly by the responsible authority acting as an executing body

The Ministry of Citizen Protection (Finance Division at Hellenic Police Headquarters) may act as the executing body of projects co financed by the European Return Fund where the project comes under its exclusive authority as the national public body and cannot be allocated to another agency or authority. According to our national legislation [articles 8, 11 and 15 of the Presidential Decree 14/2001 (Government Gazette I 12/31.01.2001)], the Ministry of Citizen Protection / Hellenic Police Headquarters / Finance Division , Aliens Division and Training Division will implement the above-mentioned action.

3.4.1.4. Expected quantified results

The results regarding the a-m action being developed and realized are expected to be the following:

- The efficient training of the police personnel on issues of returns, adapted to the needs and the standards defined by the European legislation.

- The efficient performance of the police personnel duties on return issues.

- The integrated management of returns.

3.4.1.5. Indicators to be used

Output: Number of and type of training seminars organized. Number and type of authorities trained. Number and types of topics covered. Number of participants

Outcome: Increased knowledge of international standards regarding return. Enhanced capacity of the competent authorities to deliver high quality decisions. Changes in national legislation and practices as a result of knowledge gained in the trainings.

Impact:   Effective and uniform application of common standards on return. Decrease in allegations of human rights violations in the area of return.

3.4.1.6. Visibility of EC funding

As described in point 6 of action 3.1.1. of Priority 1.

3.4.1.7. Complementarity with similar actions financed by other EC instruments, if appropriate

As described in point 7 of action 3.1.1. of Priority 1.

3.4.1.8. Financial Information

This specific project, which comes under priority 4, will receive 75% financing from Community resources (EURO 156.000,00)  and 25 % from national resources (EURO 52.000,00 from the state budget) bringing public spending on this project to EURO 208.000,00. The national contribution must be covered by the Ministry of Citizen Protection, in cooperation with the Ministries of Finance and of Economy, Competitiveness and Mercantile Marine through the Public Investment Programme (and hence the ordinary budget) and the procedure, which will be followed for the implementation of the specific action according to our national legislation and the article 11 of the implementing rules.

For every action is foreseen the below financial information:

- Trainings on return procedures of the illegal immigrants

-75% financing from Community resources: 37.500,00 €

-25 % from national resources: 12.500,00 €

- TOTAL (1): 50.000,00 €

- Trainings on escorted return procedures of the arrested illegal immigrants

-75% financing from Community resources: 9.750,00 €

-25 % from national resources: 3.250,00 €

- TOTAL (2): 13.000,00 €

- Trainings on readmission procedures

-75% financing from Community resources: 11.250,00 €

-25 % from national resources: 3.750,00 €

- TOTAL (3): 15.000,00 €

- Trainings on issues related to the protection of potential returnees' human rights

-75% financing from Community resources: 45.000,00 €

-25 % from national resources: 15.000,00 €

- TOTAL (4): 60.000,00 €

- Trainings on the treatment of vulnerable potential returnees

-75% financing from Community resources: 52.500,00 €

-25 % from national resources: 17.500,00 €

- TOTAL (5): 70.000,00 €

TOTAL (1+2+3+4+5): 208.000,00 €
4.	TECHNICAL ASSISTANCE

  - Purpose of the technical assistance

Technical assistance is a valuable tool and is vital if the projects described above are to be developed/implemented effectively. If focuses mainly on the organisation of the Responsible Authority and on the programming, design, preparation, evaluation, management, monitoring, publicity, application and control of the actions integrated under the European Return Fund and co financed from Community and national resources.

The Technical Assistance will finance measures of publicity, such as preparation of the Responsible Authority’s web site and publication of relevant data, the preparation of the procedure manuals by a consultant company, translations of programmes (Greek to English and vice versa) by authorized private offices, trainings of the Responsible Authority’s personnel, books and scientific magazines for RA’s personnel to  increase the knowledge of the RA staff on issues related to contracts, planning, evaluation, testing, implementation of EU legislation, etc., on spot checks by Unit C of the Responsible Authority and the Audit Authority, travelling expenditures of the personnel of all the designated authorities (Responsible Authority, Certifying and Audit Authority) and purchase of electronic computers (p.cs), relevant technical equipment  and consumables for the designated authorities (Responsible Authority, Certifying and Audit Authority).

Additionally, an information activity will be organized to present the achievements of the 2010 annual programme (Art. 33 (2) (a) of the Decision E (2008) 796). The implementation trail of the 2008, 2009 and 2010 APs’ actions will be presented with the references to the budget and the purpose and scope of each action. The following stakeholders will be invited to the above mentioned presentation: the leadership of the Hellenic Police Headquarters, the political leadership of the Ministry of Interior, representatives of other Ministries and international organizations and NGOs.

The Technical assistance has been calculated to be financed only (100% EC Contribution) under the Community contribution, giving the sum of EUR 800.000,00  for AP 2010.

4.2. Expected quantified results

The results expected from the use of Technical Assistance are faster implementation of the actions planned and a better standard of management, monitoring and implementation, in order to make the best possible use of Community and national resources. This will be achieved by improving the administrative and technical capacity of those involved in the management, monitoring and control system at all stages of design, programming, evaluation, management, selection, monitoring, publicity, application and control.

4.3. VISIBILITY OF EC FUNDING

As described in point 3.1.1.6.

5.	DRAFT FINANCING PLAN

| Annual Programme – Draft Financial Plan Table 1 – Overview table |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Member State: GREECE |  |  |  |  |  |  |  |  |
| Annual programme concerned: 2010 |  |  |  |  |  |  |  |  |
| Fund: EUROPEAN RETURN FUND |  |  |  |  |  |  |  |  |
| (all figures in euro) | Ref. priority | Ref. specific priority (1) | Community Contribution (a) | Public Allocation (b) | Private Allocation (c) | TOTAL (d= a+b+c) | % EC (e=a/d) | Share of total (f=d/total d) |
| Action 3.1.1.: The improvement of the information provided to potential returnees, by the employment of interpreters and translators of their languages | 1 |  | 800.000,00 | 266.666,67 | ---------- | 1.066.666,67 | 75 % | 5,64% |
| Action 3.1.2.: Reinforcement of the special office for the implementation of the readmission agreements | 1 |  | 9.000,00 | 3.000,00 | ---------- | 12.000,00 | 75% | 0,06% |
| Action 3.1.3.: The improvement of the provision of psychological support to potential returnees by employing social workers/psychologists. | 1 |  | 2.525.000,00 | 841.666,67 | ---------- | 3.366.666,67 | 75% | 17,79% |
| Action 3.1.4.: Bilateral meetings with migration authorities of the partner third countries | 1 |  | 10.000,00 | 3.333,33 | ---------- | 13.333,33 | 75% | 0,07% |
| Action 3.1.5.: Bilateral meetings with the Consular Authorities of the third countries | 1 |  | 100.000,00 | 33.333,33 | ---------- | 133.333,33 | 75% | 0,70% |
| Action 3.1.6.: Enforced/assisted returns of third-country nationals who do not or no longer fulfill the conditions for entry and stay | 1 |  | 5.076.934,40 | 1.692.311,47 | ---------- | 6.769.245,87 | 75% | 35,78% |
| Action 3.1.7.: Upgrading of the Deportation Department of Attica Aliens Division | 1 |  | 187.500,00 | 62.500,00 |  | 250.000,00 | 75% | 1,32% |
| Action 3.1.8.: Creation of pre-removal detention centre for third-country nationals who are under the procedure of return | 1 |  | 675.000,00 | 225.000,00 |  | 900.000,00 | 75% | 4,76% |
| Action 3.2.1.: The implementation of joint flights with other EU Member States | 2 |  | 300.000,00 | 100.000,00 | ---------- | 400.000,00 | 75% | 2,11% |
| Action 3.3.1.: The implementation of voluntary returns including reintegration measures | 3 |  | 3.750.000,00 | 1.250.000,00 | ---------- | 5.000.000,00 | 75% | 26,43% |
| Action 3.4.1.: Trainings of the Hellenic Police personnel | 4 |  | 156.000,00 | 52.000,00 | ---------- | 208.000,00 | 75% | 1,10% |
| Technical assistance |  |  | 800.000,00 | 0,00 | ---------- | 800.000,00 | 100% | 4,23% |
| TOTAL |  |  | 14.389.434,40 | 4.529.811,47 |  | 18.919.245,87 | 76,06% | 100,00% |

THE HEAD OF THE RESPONSIBLE AUTHORITY

KONSTANTINOS SOLDATOS

POLICE COLONEL

[Signature of the responsible person]